## BUG POINTS
S.NO | MODULE/APPLICATIONS | BUG POINTS DESCRIPTIONS | DEVELOPER STATUS | REMARKS | TESTING STATUS | TESTING REMARKS | TESTING REMARKS
1 | Section Master | After entering an existing section name, the message ‘Section name already exists’ is shown, and changing the section name still does not allow the section to be added. | Fixed |  | Verified 14/01/2026
2 | Section Master | The Section Name field should not accept spaces. | Fixed |  | Verified 14/01/2026
3 | Section Mapping | When an already added Standard and Section are selected, a message is displayed, and after changing the Section, the system does not allow saving the data | Fixed |  | Verified 14/01/2026
4 | Student Management | For discontinued student in edit mode student details are cleared | Fixed |  | Verified 14/01/2026
5 | Student Status update, student section mapping, Acadmeic Eligibility programs | Overall selection not available | Fixed |  | Verified 14/01/2026 | Now not able to test Student Section mapping
6 | Section Mapping-Edit | When multiple sections are selected while creating a new Section Mapping and the section medium is changed, all selected sections are changed. It should update only the corresponding section | Fixed |  | Verified 14/01/2026
7 | Section Mapping-order | Section Name order is not consistent and changes frequently in the Section Mapping | Fixed |  | Verified 14/01/2026
8 | Teacher Login-Student Management | Unable to add the student in the Student Management.Message displayed as"Internal server" (Currently, only the Admin portal is able to add students) | Fixed |  | Verified 14/01/2026
9 | Bulk Upload | Unable to upload bulk data. The class section is displayed as ‘Undefined’, and an error message is shown as ‘Invalid or inactive standard | Fixed |  | Verified 19/01/2026
10 | Unit,Topic | After edit the unit and topic in the list, the order changes. Now, the list is displayed based on date in ascending order. | Fixed | Now the order changes based on standard,subjectName and then orderBy column | Verified 19/01/2026
11 | Admin portal | The admin portal session logs out , even while I am using the admin portal. (One Hour Once Admin session Automatically logout ,Even I am using the Admin Portal) | Fixed |  | Reopen 02/02/2026 | 02/02/2026 Still One hrs once Admin portal session logout,Even i used this application | 03/02/2026 Now one Hrs once Not logout the admin portal
12 | Upload Video | Clicking Save without selecting a video does not show any error message. | Fixed |  | Verified 14/01/2026
13 | Upload Video | When a video is uploaded for the Tamil medium, it is also updated for both English and Tamil medium students. (Same For English medium video upload it also upload for tamil medium but tamil medium student cann't play this video) | Fixed |  | Verified 19/01/2026
14 | English Medium Student | Unable to play the Tamil subject video for English medium students | Fixed |  | Verified 19/01/2026 | Initially, the uploaded video was listed under both mediums. Now, it is listed based on the uploaded medium.
15 | Admin portal-Student management | Student Management does not display the discontinued student batch count | Fixed |  | Verified 19/01/2026
16 | Admin portal-Student management | When selecting the Discontinued Batch, students with all statuses are listed | Fixed |  | Verified 19/01/2026
17 | Student Management-Status | The Passout student option is missing in Student Management. | Not an issue |  | Not an issue
18 | Student Management | Allow deletion of student data after the student watches the uploaded video. (It's Better to Restrict Delete Action After student watch the Learning video) | Fixed |  | Verified 23/01/2026
19 | Student Management | Creating a student with previously deleted student data shows an “Internal Server Error”, while creating a new student with different data is allowed | Fixed |  | Verified 23/01/2026
20 | Subject Mapping | Changing the category does not display the corresponding subject names | Fixed |  | Verified 19/01/2026
21 | Academic Eligibility Programs | Update category Section Alignment issue in Academic Eligiblity Programs | Not an issue |  | Not an issue
22 | Academic Eligibility Programs | Previously selected standard and student name are not cleared after clicking Cancel and reopening Add Student in Academic Eligibility Programs | Fixed |  | Verified 19/01/2026
23 | Academic Eligibility Programs | After entering another standard, student name and clicking the Load button, the data does not load and no error message is displayed. | Not an issue |  | Not an issue
24 | Upload Video-Number of View | English medium student count is not displayed in the total students count in the Number of View (Example:Tamil Subject video upload) | Fixed |  | Verified 19/01/2026 | Initially, the video was listed for both medium students. Now, the video is listed based on the selected upload medium.
25 | Student portal | Thumbnail duration seconds differ from the actual video playback time. (Example:Video play duration is 5 min 34 sec, but the thumbnail shows 5 min 30 sec.Every 5second once the Second is updated in the thambnail) | Not an issue | In this the api call on five secs once,at that time only the time changes on side menu | Not an issue
26 | Student Management | After select the student status to Discontinued, edit the student details automatically changes the status to Active in edit mode. | Need to check |  | Verified 1/30/2026
27 | Student Management | After selecting the status as Discontinued, student information is missing in Student Management when viewed in edit mode. | Fixed |  | Verified 19/01/2026
28 | Student Management | When a discontinued student is changed to Active, the student information is entered but the Gender field is not displayed, so the student data cannot be updated. | Fixed |  | Verified 19/01/2026 | Initially, discontinued student information was not displayed, and when student details were entered manually, the gender was not shown. Now, discontinued student information is displayed in Edit mode
29 | Student Management | Current Academic Information should be in read only after the Save the student data. (Now it's not displayed the read only ,Can change the data without using the Edit action in the Current Academic Information) | Not an issue |  | Not an issue | In Edit mode, both edit and direct change are allowed for the current academic information. Once the current academic information is changed, the Add Row option is selected
30 | Student Management-View | Student data is not shown in the View action for discontinued students. | Fixed |  | Verified 14/01/2026
31 | Video Streaming Report | Select Date Range displayed as Two Date calander | Not an issue |  | Not an issue
32 | Video Streaming Report | Select date range and select cancel but date range filter applied | Fixed |  | Verified 20/1/2026
33 | Upload Videos | Published videos Should not be allow edit Action. (Now allow Edit for published videos but Not allowed to Delete the Published Videos) | Fixed | NEED TO DISCUESS Now won't allow to change anyfield in edit mode for published video,only allow to change the status | Verified 20/1/2026 | Now only Status is changed in Edit Mode,Other fields are Read only
34 | Upload Video-Edit | After editing the published video and changing the medium from Tamil to English, the video is displayed in the english medium Student Portal, but students are not able to play the video. (Edit is done then select publish action but the video is not able to play) | Fixed | Now won't allow to change anyfield in edit mode for published video | Verified 20/1/2026 | Now Not able to edit for the Published videos Once inactive upload video then Able to edit the upload video
35 | Upload Video-Edit | When the video name is too long and saved, the video name overlaps in the upload video section. | Fixed |  | Verified20/01/2026
36 | Upload Video-Edit | After editing the Upload video and clicking the Update button without selecting the Publish action, the video is updated in the Student Portal. (It is better to display the changes in the Student Portal only after editing the published video and re-publishing it) | Fixed | Now once the video is published it wont allow to republish again it in edit mode,only change the status of the video | Verified 20/1/2026 | Now once video is published then Publish Action is hide Publish is enable once inactive and Active the status then the Publish is enabled
37 | Upload Video-Status Filter | the Upload Video Status filter dropdown, three statuses are displayed: Published, Not Published, and Inactive. However, currently only Published and Not Published videos are Checked | Fixed |  | Verified 20/1/2026
38 | Upload Video | If the video is uploaded without saving and only the Publish button is selected, the video gets published | Fixed | Now shown the publish button only in edit mode | Verified 19/01/2026
39 | Student portal | After playing and pausing the video, the paused video topic is not displayed in the Resume Learning section | Fixed |  | Reopen 23/01/2026 Verified 30/01/2026 | Still video is not listed in the Continue learning | 30/01/2026 Now Video is Listed in the Resume learning
40 | Section Master | Section Master Accepts Special characters | Not an issue |  | Not an issue | Now there is no rstriction in Section Master
41 | Re-order units &Topic | When reordering units and topics for the Tamil Medium, the order is also changed for English Medium students (The Unit and Topic texts for both English and Tamil mediums are entered on a single page, reordering affects both mediums. It is better to remove the medium option in the Reorder section) | Fixed | Now the below content is only changed | Verified 29/01/2026
42 | Re-order units &Topic | In the Reorder Units and Topics section, under the Curriculum and Extra Curriculum category, the subcategory type should be read-only | Fixed |  | Verified 20/01/2026
43 | Re-order units &Topic | Extra Curriculum Category Unit and Topic is not listed in the Re-order Unit &Topic section (Already unit and Topic is created ) | Fixed |  | Verified 19/01/2026
44 | Subject Mapping-Edit | While editing the standard in subject mapping, when the Curriculum category is changed to Extra Curriculum, no subject names are listed initially; after selecting the standard, the subject names are displayed | Fixed |  | Verified 20/01/2026
45 | Subject Mapping-Edit | While editing the standard in subject mapping, the previously added Extra Curriculum subject is not displayed in the mapping summary | Fixed |  | Verified 20/01/2026
46 | Subject Mapping-Edit | Unable to add multiple subjects to the Extra Curriculum category. An error message is displayed: ‘Class subject mapping already exists | Fixed |  | Verified 20/01/2026 | Once at least one subject is mapped, changes can be made only in Edit mode.
47 | Subject Mapping | When adding Extra Curriculum mapping for an existing standard, the message ‘Class subject mapping already exists’ is displayed | Fixed |  | Verified 20/01/2026 | Now Multiple Subject added in the save time.OR Edit the existing Mapping and add the subject
48 | Subject Maping-Edit | After adding the co-curricular subject mapping and editing it, the previously selected subject under the co-curricular category is not displayed in the Mapping Summary section. | Fixed |  | Verified 20/01/2026
49 | Subject Mapping-Edit | After adding the co-curricular subject mapping and editing it, when the subject is selected again and updated, the standard data is missing in the Subject Mapping. | Fixed |  | Verified 20/01/2026
50 | Upload video | The subject name is displayed twice in the Subject Name dropdown field. | Fixed |  | Verified 23/01/2026
51 | Upload Video | When Tamil Medium is selected, the subject dropdown does not display the Tamil subject names. | Fixed |  | Verified 20/01/2026
53 | Students | Current Academic Information should allow only the current academic year, not past years. | Fixed |  | Verified 20/01/2026
54 | Video Streaming Report | Video Streaming report is Displayed based on the Category wise (Now Student watch time is displayed as overall watching time) | Not an issue
55 | Student Management | The Updated By column does not display the created or updated teacher name. When the admin creates the record, the admin name is displayed in the Updated By column. | Fixed |  | Verified 29/01/2026
56 | Student Management Admin,Teacherportal | In the Filter and Add Student screens, the order of options in the Section and Medium dropdowns has changed | Fixed |  | Verified 20/01/2026
57 | Academic Eligibility Programs Curriculum And Extra Curriculum | First, student is selected from one section, then another student is selected from a different section. The student count is shown for both sections in the Academic Eligibility Program, but after saving, the student count is displayed only for the last added section. (When using the Section and Medium filters, the first added student is not displayed) | Fixed | Now when click reset that time the first selected student count also cleared | Reopen 20/01/2025 Verified 23/01/2026 Verified 27/01/2026 | Now Select student from one section then Select student from another section previous student count is not cleared
58 | Subject Mapping | In the Subject Mapping section, after adding the Tamil subject first and Select another subject and saving, the subject order is displayed based on the English subject name in ascending order, and then the Tamil subject name is displayed. | Not an issue
59 | Number of View | Number of view count is displayed Wrongly (Only one student watched the Video then the count is displayed as 3) Example:English medium video upload then upload tamil medium Video for the same subject then the View count differ ) | Fixed |  | Verified 23/01/2026
60 | Upload Video | Inactive Status work flow is not in the Upload video | Fixed |  | Verified 20/01/2026
61 | Student portal | In the Continue Learning page, a single video is displayed multiple times (Example:After uploading an English-medium video and one student viewing it, a Tamil-medium video is uploaded; before publishing, the Tamil-medium video shows a view count of 1, and the video is displayed multiple times in the student portal.) | Fixed |  | Verified 23/01/2026
52 | Teacher Login | When a teacher is assigned to a particular standard, uploading students from another standard should not be allowed. (Both Excel and Add student) | Fixed | Only fixed for Individual add | Verified 29/01/2026 | Now Only Individual Student Added in the teacher portal
62 | Upload Video-Number of View-Total Students count | In the Total Students count is Displayed Wrongly (Total:6 students,2discontinued but the Total student count is displayed as 5) | Not an issue | Need to discuss with mala akka for discontinued student count
63 | Add student | When an active student is changed to discontinued in Edit mode, the academic history is updated and shown as a single record (However, when the student status is updated through the Student Status Update page, separate Active and Discontinued academic records are displayed.) | Fixed | Now in add mode only active status are set, but in edit mode multiple rows are added along with discontinued status | Verified 23/01/2026 Verified 27/01/2026 | Now Select student from one section then Select student from another section previous student count is not cleared Now Active and Discontinue status displayed separately
64 | Academic Eligibility Programs | Savethe Academic Eligibility Programs message displayed as Student status updated successfully | Fixed |  | Verified 1/23/2026
65 | Upload Video-Inactive Video | If the video is listed under the Continue Learning list, when a video is marked inactive, it is not shown under the subject, but it is still clickable in the Continue Learning list and does not play because it is inactive. (It's Better to Remove the Continue Learning List once inactive the Published video) | Fixed |  | Verified 27/01/2026
66 | Upload Video | After uploading and publishing a new video, the previously inactive video’s resume timing is still applied when the video is played. (If the resume video is not listed, the new video starts from the beginning.) | Fixed |  | Verified 27/01/2026
67 | Academic Year-Revert Action | Current Academic Year Revert Option is not displayed in the Academic Year | Fixed |  | Verified 1/23/2026
68 | Academic Year | Previous year student data Empty (It's set to the Backend team) | Fixed |  | Verified 1/23/2026
69 | Students | Now Academic Year and Month Updated but Previous year Student Data is Empty.so Cannot be test the Rollout | Fixed |  | Verified 1/23/2026
70 | Student Section Mapping | Now Academic Year and Month Updated but Previous year Student Data is Empty.so Cannot be test the Student Section Mapping | Fixed |  | Verified 1/23/2026
71 | Video Streaming Report | When a student watches the video for the first time, the video streaming report shows the actual video duration. When the same student watches the video again, the streaming report displays only the second-time watch duration | Fixed | Fixed on 30/01/2026 | Reopen 29/01/2026 Reopen 30/01/2026 Verified 30/01/2026 | Now Once Student Completed and Again student watched the Same video if the Total Watched time is displayed as the Second time watched time (This point already discussed with Mala and Shanthi. Once the student completes watching the video, the time and Status is not changed.) | 30/01/2026 Still issue Second time student watched video admin report student watched time changed | 30/01/2026 After deployment Now the Watched time is not changed for the second time
72 | Section Mapping-Edit | After creating the section mapping with a group and saving the data, the group name is not displayed in Edit mode. | Fixed |  | Verified 1/27/2026
73 | Upload Video-Inactive Video | Inactive Video then Able to delete the Upload Data | Fixed | Need to discuss | Discussed 20/01/2026 | Inactive videos can now be deleted to avoid unwanted junk data; hence, deletion is allowed
74 | Section Mapping | Current Academic year section mapping is unable to delete (Example:2025 June to 2026 January 2026 January to 2027 2026 Academic year Unable to delete) | Need to Recheck |  | Data cleared unable to reproduce | Now Subject is mapping to the std .then message displayed
75 | Academic Year-Roll Out | Roll out Action is not displayed in the Academic Year | Fixed |  | Verified 1/23/2026
76 | Unit Master-Filter | In Unit Master, when the Curriculum or Extra Curriculum category is selected, the Category Type field is disabled (While adding a unit in Unit Master, if the Curriculum or Extra Curriculum category is selected, the Category Type field is disabled.) | Not an issue | Filter based on figma design
77 | Subject Mapping | After changing from Curriculum to Co-curriculum/Extra-curriculum and saving, the previously selected Curriculum subject is not cleared, so it appears in the Co-curriculum category list. (It is better to clear the previously selected data when the category is changed before saving the subject mapping.) | Fixed |  | Verified 1/23/2026
78 | Subject Mapping | Once the category type is selected, the subject name is listed.Otherwise not displayed the Subject name | Fixed |  | Verified 1/23/2026
79 | Upload Video | VII and VIII Std Subject name displayed Multiple Times in Upload video section | Fixed |  | Verified 1/23/2026
80 | Group | The group can be inactivated even though subjects, units, and topics have already been created for this group. | Fixed |  | Verified 1/27/2026
81 | Section | The section can be inactivated even though it is already mapped to the standard. | Fixed |  | Verified 1/27/2026
82 | Students | Student current Academic Information Date field is should be allowed for Current Academic Year and Month (Example:Academic Year 2025 June to 2026 January but select the 2025 January Month allowed ) | Not an issue
83 | Student | Drag video to end, status updated as completed when i try to play again last few seconds loaded and then play button present | Not an issue
84 | Student | In the above case if i play the video again status remains completed | Not an issue
85 | Admin portal -- Student management | Change Discontinued student to active discontinued data not retained | Fixed |  | Verified 1/23/2026 | Having issue in date
86 | Admin portal -- Student status update | Search works only for name | Fixed |  | Verified 1/23/2026
87 | Academic Eligibility Programs | Click on student count -- Hide search & reset button | Not an issue | Not an issue
88 | Subject | Already existing inactive subject name is enter then the message displayed as "Subject Tamil name already exists" (I enter Both english and Tamil subject name for already existsing name) | Not an issue |  | Reproduced
89 | Group | Multi-select standard is added, but the data is not displayed separately | Not an issue
90 | Group | Duplicate English names are not validated.Only Tamil group names are Validated | Fixed |  | Verified 1/27/2026
91 | Co-curriculum category | not allow creation of an inactive Co-curriculum category with the same name | Not an issue
92 | Standard | Remove the Standard Sorting | Fixed |  | Verified 1/27/2026
93 | Admin portal -- Student status update | Design issue — Search by — display no records found | Fixed |  | Verified 1/23/2026
94 | Academic Year | Year 2026-2026 Start year --> January - 2026 End Year --> December -2027 | Fixed |  | Verified 1/23/2026
95 | Academic Year | Year sorting based on month not year (Sort by ascending list December -2027, January -2025) | Fixed |  | Unable to test now
96 | Overall | Popup auto close | Not an issue | Give an manual close for confirmation modal, For delete confirmation give an cancel instead of close icon
97 | Academic Year, Standard | Search and filter not working for Updated by | Fixed |  | Verified 1/23/2026
98 | Subject Mapping-Edit Inactive Subject select | inactive subject name is displayed in the Edit mode but newly added subject mapping at that time inactive subject name is not displayed (Example:Social sciencee Subject is inactive but in edit mode it is displayed) | Fixed |  | Verified 1/27/2026
99 | Group delete | After section maped to group it get deleted, mapping remains try to delete throws Class section mapping not found | Fixed |  | Verified 1/30/2026
100 | Section mapping-Delete | After subject mapping section mapping can be deleted | Fixed |  | Verified 1/29/2026
101 | Group add | Select multiple standard -- Design Wrap issue-- Std wrapped out of dropdown | Fixed |  | Verified 1/23/2026
102 | Subject Mapping-Edit subject name | Deselect the Subject name check box in edit mode.Once if the Subject is already published (It's better to restrict once upload the video then the subection mapping not selecte the previously selected subjects) | Fixed | Now shown toast message ,if user deselect the used subject | Verified 1/29/2026
103 | Group edit | After Subject mapping able to change the standard -- Note subject mapping remains unchanged | Fixed |  | Verified 29/01/2026
104 | Group filter | Copy & Paste not working -- அறிவியல் value not accepted in filter Group name | Fixed |  | Verified 1/27/2026
105 | Section | Page title display as Section Master | Not an issue | Same as in figma
106 | Unit | Inactive group listed in add unit | Fixed |  | Verified 1/29/2026
107 | Section mapping | Based on selected standard disabled Group dropdown | Fixed |  | Verified 28/01/2026
108 | Section | Once Section is mapped to the student then the Section is should not be allow Inactive (Now student is mapped to the Section,then inactive Section then check the student detail section is missing ) | Fixed |  | Verified 1/27/2026
109 | Add Teacher Profile | Inactive Subject name is listed in the Subject Expertise Section in the Add teacher profile | Fixed |  | Verified 1/23/2026
110 | Teacher Management-Edit | Update Teacher information then the Message displayed as "Updated sucessfully" instead of "Teacher Information Updated successfully" | Fixed |  | Verified 1/23/2026
111 | Teacher Management-Edit | Select Inactive Batch displayed all the Active and Inactive Teacher | Fixed |  | Verified 1/23/2026
112 | Student portal | Subjects are not listed | Fixed |  | Verified 1/22/2026
113 | Unit | After a video is published, the corresponding unit is should not be allow inactive status | Fixed | Need to discuss | Discussed 22/01/2026 Verified 29/01/2026 | Now inactive Unit and topic is listed in theStudent portal Now need to check after fixing Inactive status ,once Inactive unit /topic then the video is not listed in the Student portal
114 | Topic | After a video is published,the corresponding Topic is should not be allow inactive Status | Fixed | Need to discuss | Verified 1/29/2026 | Need to check after fixing
115 | Student portal | After a video is published, if the associated unit or topic is inactive, the related video is not listed in the student portal. | Fixed |  | Verified 27/01/2026 | Once Published video unit is inactive then the student portal get White screen .Once open in another tab student portal opened
116 | All Page | inactive name should be allowed to be created again in the Add Section. | Not an issue
117 | Number of views | After select the Watched student count then the Header displayed as" videos->Number of views VII " (It's Better to Remove the Std displayed in the Number of view section after select watch student count/Displayed the Number of views count ) | Fixed |  | Verified 27/01/2026
118 | Student portal | Once a student completed to watching a full video, if they watch the same video again for some time, the video is not listed in the Continue Learning section. | Fixed | Need to discuss | Verified 1/30/2026
119 | Student portal | Seconds are not included in video timing | Fixed |  | Verified 29/01/2026
120 | Student portal | If a video is inactivated by the admin while a student is watching it, and the same topic video is re-uploaded and published again, the view count and Continue Learning status are taken from the previously inactive video. | Fixed on 28/01/2026 |  | Reopen27/01/2026 Verified 30/01/2026 | Now Inactive and upload new video in edit mode now the the video is listed in the Continue learning for the previous Inactive video Timing | Now If the student Watched the video then inactive but not replaced the Video but newly added the video for the same topic Once There is any student not watched then able to replaced the Topic for the video
122 | Subject-- Search, Filter, Sorting | வேதியியல் search by and filter not working | Fixed |  | Verified 1/27/2026
123 | Unit | Status sorting fails | Fixed on 30/01/2026 |  | Verified 1/30/2026
124 | Subject | Same subject can be added under Curriculum, Co - Curriculum, Extra Curriculum, while search subject under Curriculum only listed Basded on category search and filter appears | Not an issue
121 | Section mapping- Search | கணினி அறிவியல் search not working for tamil | Fixed |  | Verified 1/27/2026
125 | Roll out | Student details are not loaded in Review student status | Fixed |  | Verified 1/27/2026
126 | Roll out | After Rollout then Student section mapping One student slect and Promoted to next standard again select the Student section mapping prompted student data is listed | Fixed on 30/01/2026 |  | Verified 31/01/2026
127 | Rollout-Student edit and view | Student Current academic details Current Academic Status should be active and Previous Academic status should be Prompted | Fixed |  | Verified 1/27/2026
128 | Student section mapping | Select XII standard XI std old section not loaded | Fixed |  | Verified 1/30/2026
129 | Student section mapping | Student section mapping Change to Next section drop down displayed Multiple times | Fixed |  | Verified 1/27/2026
130 | Student section mapping | Previous selected Std and Section not cleared | Fixed 03/03/2026 |  | Reopen 1/31/2026 Reopen 02/02/2026 Verified 03/03/2026 | 02/02/2026 Still bottom of the Section is not cleared | 03/02/2026 Now Selected Std and Sec is cleared once change the std
131 | Upload Video-Number of view count | Student prompted to next section then the corresponding std videos are listed Number of view count is not changed after the roll out and then student watch the Current academic video | Fixed |  | Verified 30/01/2026
132 | Upload Video-Number of view count | Previous Academic Watched video student details are not Viewed (It's better filter option include for view the previous year number of view student ) | Fixed | Fixed on 30/01/2026 | Verified 1/31/2026 | After Rollout Previous Academic videos Number of views count and watched Student count and Total student count is mismatched
133 | Revert Option | After Roll out and then student mapped to the Next section and student watched video but the Revert Action is displayed in the Current Academic Year | Fixed |  | Verified 1/27/2026
134 | Student section mapping | One student mapped to another section , again that student listed and mapped to another section and student page filter by standard not working | Fixed | Student Page status filter is work for me | Verified 1/30/2026
135 | Review Student status | In review Student Status Select the Section and medium drop down then navigate to the Next field Selected Section cleared | Fixed |  | Verified 1/30/2026
136 | Review Stdent Status | Selcted std but not select the Load button close the Pop up again open the Review Student status previously selected Data is not cleared .once Reset is selected then the previous data is cleared | Fixed |  | Verified 1/27/2026
137 | Student section mapping | After the rollout, discontinued students are listed in the Student section mapping. | Fixed |  | Verified 1/27/2026
138 | Student section mapping | Discontinued students appear as duplicate entries in the section mapping. | Fixed |  | Verified 1/27/2026
139 | Students-Status | After the rollout, discontinued students are displayed as Active in the list, but in Edit and View modes, their status is shown as Discontinued | Need to Recheck |  | Verified 31/01/2026 | Now Discontinued students status is displayed correctly
140 | Students | After the rollout, check the student status before section mapping; the discontinued student information is cleared/Empty | Fixed |  | Verified 1/30/2026
141 | Students-Active and Discontinued Student | After the rollout, the Active/Discontinued student information data is cleared in the Student Information section | Fixed | Fixed on 30/01/2026 For Roll Number | Verified 31/01/2026 | Roll Number missing in view Reopen 1/30/2026 | 31/01/2026Now roll number is displayed
142 | Student | After the rollout, once the student section mapping is completed, the student roll number data is cleared/Empty | Need to check |  | Verified 31/01/2026 | 31/01/2026Now After Roll out Roll number and EMIS Number is listed in both edit and view mode
143 | Student-Prompted Status | After the rollout, if a student’s status is displayed as Active and the student is mapped to the next section, the Promoted status is shown in Edit and View modes but not displayed on the list page | Need to Recheck |  | Verified 31/01/2026 | Now Student prompted status is displayed in edit and view
144 | Student-Passed Out Status | Promoted status not displayed on list page when Pass Out status is shown. | Not an issue
145 | Section Mapping | After Rollout previous year mapped section is not listed in the current academic year list .Then check the newly mapped for the Current academic year message displayed as "Class section is already exists" | Fixed |  | Verified 1/27/2026
146 | Edit video -- Inactive | Restrict standard& group and subject change for inactive video | Fixed |  | Verified 1/27/2026
147 | Student | After bulk uploading students, the current academic student status date is displayed as the current date (Example:Current academic year Jan2025 to Dec 2025 Upload excel Current academic student date is displayed as current date 23/01/2026) | Fixed on 30/01/2026 |  | Verified 01/02/2026 | 30/01/2026 After Deployment Still Bulk upload student date of joing displayed as current dateReopen 30/01/2026 | 1/2/2026 Now Bulk upload Excel Date of Joining is there Date of joining is allowed with in the Academic year Example :Jan 2025 to Oct 2025 Jan 2026 to Oct 2026 Date of Joining is allowed upto dec 2026
148 | Student status Update | When changing an active student to Discontinued status, the status date should not allow a future academic year date. | Fixed |  | Verified 28/01/2026
149 | Student portal | Co-Curriculum subject not listed, Extra curriculum also not listed | Need sample | Fixed | Verified 30/01/2026 | Now Co curriculum and Extra curriculum Subjects are listed
150 | Add unit-Standard and group | Same group name is displayed muliptle times | Fixed |  | Verified 29/01/2026
151 | Video -- Filter | After choosing subject name Medium get disappear, for Co-Curriculum Unit dropdown not listed | Fixed |  | Verified 1/27/2026
152 | Teacher Management | After Roll out if the Teacher Current Academic information Teacher standard changed (Example:Current academic information:2025 to 2025 VII -C Teacher Mapped After Rollout current Academic Information:2026 to 2026 VIII-C Teacher displayed) | Fixed |  | Verified 1/27/2026
153 | Section Mapping | After rollout, when the previous academic year is selected, the Edit and Delete actions should not be listed | Fixed |  | Verified 1/27/2026
154 | Student section mapping | After section mapping, again all students are listed for again section mapping | Fixed | Current section column included | Verified 1/30/2026
155 | Studet section mapping | After selecting a standard and old section and mapping students to the next section, the old section is cleared. When a different standard is selected, the previously selected old section is automatically displayed; after mapping to another section, the old section is cleared again | Fixed |  | Verified 1/27/2026
156 | Student-Edit Academic information | Current Academic year Edit current academic information is updated for the same status then displayed in same line.Now displayed as separate line. This imapct After roll out Student section mapping Student name duplicated (Example:10/06/2025 active then edit Change the Date 20/06/2025 Now displayed as Two line with active status) | Fixed |  | Verified 29/01/2026
156 | Student-Edit Academic information | Student status changed to Discontinued and add the data then edit the Discontinued data change the Date and add.It's should be updated on the already discontinued data Not displayed the separate line.Now displayed multiple times for the same status | Fixed | Fixed on 30/01/2026 | Verified 1/30/2026 | When teacher bulk-uploads student data and later changes the student status to Discontinued in edit mode, the current academic information order changes because the bulk upload date is the current date and the discontinue date is 2025. In this case, without any changes, just clicking Update shows the student status as Active in the list, edit, and view modes
157 | Exam Type | Search and Filter is not in the Exam type | Fixed |  | Verified 1/27/2026
158 | Admin -- Student management | Total student 80 Active 78 inactive 0 display active for 80 records in list, download excel it display Promoted for 2 student Divya & Shreya List display 76records only | Fixed |  | Verified 1/30/2026
159 | Admin | User Role, User Master -- No Search & filter option | Fixed |  | Verified 1/27/2026
160 | Admin | Academic Eligibility Programs -- No search option | Not an issue
161 | Admin -- User Master | Add User for Teacher role, unable to login as teacher | Fixed | User role only shown the admin | Verified 28/01/2026 | Now User role is only for Admin
162 | Admin -- Teacher Managment | After rollourt add student for VIII - B delete VIII-B teacher , teacher get deleted without any message | Not an issue
163 | Admin -- Teacher Managment | in the above case Create same teacher again , alert msg thrown as User name already exists | Fixed |  | Verified 28/01/2026
164 | Admin -- Subject | give subject name and select category subject name disappears | Fixed |  | Verified 1/28/2026
165 | Group | After subject mapping restrict group inactive (Without group section mapping) | Fixed |  | Verified 1/28/2026
166 | Exam Type | Exam type in tamil not listed | Fixed |  | Verified 1/29/2026
167 | Section Mapping -- Medium change | section map --> X-A tamil add student now in edit mode change medium as English. Medium get updated | Fixed |  | Verified 1/29/2026
168 | Published video -Student portal | After publishing the video, it is listed only for one student; students from another section cannot Displayed the video. (Example:X -B One student watched Second student video not listed and Another sec student also video not listed) | Need sample |  | Unable to reproduce
169 | Roll out -- Student Preview | Section and medium get cleared unable to filter by section | Fixed |  | Verified 1/30/2026
170 | Rollout | After Roll out Previous discontinued student alsoPrompted to next standard, XI- Nursing student promoted to XII-- Nursing but XII--Nursing student status not changed (Added before rollout) Studentlist -- Discontinued student also listed, Previous year X,XII students not listed, total student count mismatched | Need to Recheck |  | Verified 2/2/2026
171 | Rollout | After Roll out , student list pagination display 1-135 but list only 75students | Fixed on 30/01/2026 |  | Verified 31/01/2026
172 | Rollout | After rollout acadmeic details both current & previous not listed for teachers but current acadmecic details not listed for X & XII teacher | Fixed |  | Verified 02/02/2026 | Still Current academic teacher Information is not listed Reopen 31/01/2026 | 02/02/2026 After roll out Teacher Academic information is displayed for all teacher
173 | Revert Option | After acadmecic revert student status updated as multiple times in edit & view mode | Need to Recheck |  | Reopen 02/02/2026 | 02/02/2026 After revert,Discontinued student Academic details displayed as two entry for same Status | Need to recheck 03/02/2026
174 | Revert Option | After revert students status displayed as Promoted and Passed out in the list.(Discontinued student status display as Promoted) | Fixed on 30/01/2026 |  | Verified 2/2/2026
175 | Rollout-Student section mapping | Impact of previous point, when again rollout students are not listed because no Active student so unable do section mapping | Need to Recheck |  | Verified 2/2/2026
176 | Upload video -- Filter | Previous and current year displays same no of views count, if student watch video, view count updated in previous year too | Fixed | Fixed on 30/01/2026 | Verified 2/3/2026 | Now Current academic student watched the video then the Previous year upload video Number of Total student count updated
177 | Upload video - current acedmeic year | No of view count should be zero | Fixed |  | Verified 30/01/2026
178 | Student Management -- After rollut | Batch count displaying wrongly Active shows 5 on click 1 record loaded | Fixed on 30/01/2026 |  | Verified 1/31/2026
179 | Student Management -- After rollut | Unable to delete student after rollout Student cannot be deleted because video activity exists for this student alert msg thrown but student not mapped to section (Consider previous acadmeic year count) | Not an issue |  | Student should not deleted
180 | Academic Eligibility Program-After Roll out | After roll out Previous mapped student is not listed in the Academic eligibility Program but in the list student mapped student count is listed, Filter by VIII std,XII-Computer science, Co-curricculam Health Camps and Campaign not listed | Fixed |  | Verified 2/3/2026 | Having issue Academic Year reset to 2026 - 2026 automatically while applying filter in Academic Eligibility Programs
181 | Student Management -- Sorting | Section and medium sorting fail | Fixed | Fixed on 30/01/2026 | Verified 1/30/2026
182 | Student status update, Student section mapping | EMIS search not working | Fixed |  | Verified 1/30/2026
183 | Teacher Management | Add XI-A teacher for Biology group, unable to add XI-A teacher for commerce group | Fixed |  | Verified 1/29/2026
183 | Unit and Topic | VI to X standard not loaded in the standard drop down | Fixed |  | Verified 1/29/2026
184 | Academic Eligibility Programs | Map JEE Advance program to all XI - Biology B1 Tamil students, duplicate entry created for XI- Commerce with same count on click student data not loaded | Fixed |  | Working fine
185 | Result Management | Need to hide Grade label if Grade is not updated in result excel, i give rank but rank column not updated, XI-A Biology result displayed in XI-A Commerce teacher login too XI-A Commerce result displayed in XI-A Biology teacher login | Fixed on 30/01/2026 |  | Verified 1/31/2026
186 | Subject Mapping | XI- A Biology and XI-A Commerce subject mapping missing (Note : Extra curriculum added for XI-A Biology) | Fixed on 30/01/2026 |  | Verified 1/30/2026
187 | Rollout | Search by EMIS number fail in Rollout Popup | Fixed on 30/01/2026 |  | Verified 1/30/2026
188 | Rollout -- Video upload | Upload Video— Need to remove edit & delete for previous Academic year | Fixed on 30/01/2026 |  | Verified 1/31/2026
189 | Academic Eligibility Programs | After rollout , previous Eligibility Programs should not list in current year | Fixed |  | Verified 2/3/2026
190 | Student section mapping | X std mapping to XI group | Fixed |  | Verified 2/3/2026 |  | s
191 | Academic Eligibility Programs | After rollout add Extra-Curriculum not listed, Academic eligibility mapped successfully for selected students 1 records skipped. | Fixed |  | Verified 2/2/2026
192 | Result Management | Standard filter not working | Fixed |  | Verified 2/2/2026
193 | Student Portal | After Roll out ,Change the Academic Year ,Student previous year Result is not Displayed | Fixed |  | Verified 2/2/2026
194 | Student Portal | Video not played | Fixed |  | Verified 2/2/2026
195 | Result Management | Need to hide Revert button for previous academic result | Fixed 03/03/2026 |  | Verified 03/02/2026
196 | Student | After revert,Discontinued student count Miss match VII TO X std Discontinued student not listed
197 | Student | After revert,Discontinued student Status Displayed as Active
198 | Admin portal -- Student list | Updated by displaying wrongly for 10 th mapping | Fixed 03/03/2026 |  | Verified 03/02/2026
199 | Eligibility Prg | Eligibility Programs — Section & medium duplicated | Fixed 03/03/2026 |  | Verified 2/3/2026
200 | Student section mapping | After roll out 10 std student partially mapped to 11 std again student section mapping mapped students are not listed | Fixed 03/03/2026 |  | Verified 2/3/2026
201 | Academic Eligibility Program | After Roll out ,Previous year student mapped to Eligilibity Program and roll out current year Student not mapped to the section mapping but the eligibilty program student count displayed but inside there is no student records | Need to check after section mapping
202 | Section Mapping | After Roll out ,Current academic section mapping is unable to delete because Previous year subject mapped to this class | Need to Discuss
203 | Section Mapping | After Rollout 10th student partially mapped to the XI Std Again map the Xth std ,already mapped student is not listed in the Section mapping | Fixed |  | Verified 2/3/2026
204 | Academic Eligibility Program | Previous year Extra curriculum same subject is mapped tothe VI ,and VII std After roll out and Extra curriculum student is mapped to the next section but Eligbility Program is not listed for the Current year | Fixed 03/03/2026 |  | Verified03/02/2026 | Now same subject is mapping ,After the rollout Eligibility programs listed automatically with the previous year count and inside there is no student record. Once section mapping then the student data is listed in the eligibility programs
205 | Video upload | Apply filter 2025 , click on student count move back acadmeic year reset to 2026 | Fixed 03/03/2026 |  | Verified 2/3/2026
206 | Video upload | co curriculam, extra curriculam total studnet list all students count, it should list only mapped student count | Fixed 03/03/2026 |  | Verified 2/3/2026
207 | Section Mapping | X discountinued student listed in section mapping Nandita --2002765295, Malini -- 2002765297
208 | Video upload | Preview video not played | Fixed 03/03/2026 |  | Verified 2/3/2026
205 | Academic Eligibility Program | Subject name duplicated in filter | Fixed 03/03/2026 |  | Verified 2/3/2026
206 | Academic Eligibility Program | 2025 to 2026-IX-NEET, X-JEE Mapped 2026 TO 2027 -Xth Co-curriculum is not listed in the eligibility program list page but student portal previous year student co-curriculum is listed and student partially watch the video but not listed in the resume learning | Fixed 03/03/2026 |  | Reopen 03/02/2026 Verified 03/02/2026 | 03/02/2026 Still x std student Previous year NEET Co curriculum is listed | 03/02/2026 Now Not listed the Co curriculum becaus IX-NEET,NOW XTH JEE co-curriculum is mapped
207 | Student portal | Student resume learning list page Student watched 4 videos ,displayed order correctly,Once 5th subject watched at that time First video remove from the top 4 list Again watch the Remove subject video is not updated in the Top 4 List ,At that same time Top 4 list play any video not Update the List page. ( Resume Video is watched again then not updated the top 4 list.Once Watched new topic video then the Top 4 list is updated) | Fixed 03/03/2026 |  | Verified03/02/2026
208 | Video upload | When unsupported file added/ More than 500 MB file added alert message not shown it displays Upload fail | Fixed 03/03/2026 |  | Verified 2/3/2026
209 | Student portal-Extra curriculum -Multiple subjects Listed | After roll out, previous year Eligibility student listed in the Current year,But Multiple subjects are displayed in theStudent portal (Example:VI-Carom VII-Carom,drawing Multiple subjects added After rollout,Previous year VI carom eligbility student is listed in the current year .In student portal subject displayed as Carom and Drawing but i mapped the student for carom only) | Fixed 03/03/2026 |  | Verified03/02/2026

## Checklist
Academic Year
Pevious Academic year | Roll out option | Fail | Student not loaded
Current Academic year | Revert option | Fail | Student not loaded
Search |  | Fail | Updated by fail
Filter |  | Fail | Updated by fail
Sorting |  | Pass
Pagnination |  | Pass
Standard
Search |  | Fail | Updated by fail
Filter |  | Fail | Updated by fail
Backend data Vi- XII |  | Pass
Sorting |  | Fail | Remove sorting
Pagnination |  | Pass
Group
Add |  | Fail | Group name in english duplicate not validated
Edit |  | Fail | After Subject mapping able to change the standard -- Note subject mapping remains unchanged
Delete |  | Fail | After section maped to group it get deleted, mapping remains try to delete throws Class section mapping not found | can be deleted before subject mapping
Search |  | Pass
Filter |  | Fail | Tamil font not accepted in Group name field (Copy & Paste not working)
Sorting |  | Pass
Pagnination |  | Pass
Section
Add |  | Pass
Edit |  | Pass | After section mapping , section name can be updated need to check impact on student - get updated
Delete |  | Pass
Search |  | Pass
Filter |  | Pass
Sorting |  | Pass
Pagnination |  | Pass
Section Mapping
Add |  | Fail | multiple select — class section mapping already exist general msg thrown
Edit |  | Pass
Delete |  | Pass
Search |  | Fail | கணினி அறிவியல் not working
Filter |  | Pass
Sorting |  | Fail | Status
Pagnination |  | Pass
Co-Curriculum Category
Add |  | Pass
Edit |  | Pass
Delete |  | Pass
Search |  | Pass
Filter |  | Pass
Pagnination |  | Pass
Sorting |  | Pass
Subject
Add |  | Pass
Edit |  | Pass
Delete |  | Pass
Search |  | Fail | வேதியியல் -- not working
Filter |  | Fail | வேதியியல் -- Subject name display no record, give subject name and select category subject name disappears
Pagnination |  | Pass
Sorting |  | Pass
Subject Mapping
Add |  | Pass
Edit |  | Fail | After video upload restrict subject unmapping
Delete |  | Pass
Search |  | Fail | Extra-Curriculum search not working
Filter |  | Fail | Enable category type only for Co-Curriculum
Pagnination |  | Pass
Sorting |  | Pass
Unit
Add |  | Pass
Edit |  | Fail | After video upload restrict unit inactive
Delete |  | Pass
Search |  | Pass | Search by Active list Inactive too
Filter |  | Pass
Pagnination |  | Pass
Sorting |  | Fail | Descending status fail
Topic
Add |  | Pass
Edit |  | Pass
Delete |  | Pass
Search |  | Pass
Filter |  | Pass
Pagnination |  | Pass
Sorting |  | Fail | Descending status fail
Videos
Add |  | Pass
Edit |  | Fail
Delete |  | Pass
Search |  | Pass
Filter |  | Fail | After choosing subject name medium get disappeared
Pagnination |  | Pass
Sorting |  | Pass | Sorting occurs for Not published, then standard wise
Publish |  | Pass
Reorder |  | Fail | Remove medium
Video streaming |  | Fail
Exam Type
Sorting |  | Fail
Pagination |  | Fail
Search |  | Fail
Filter |  | Fail
User Role
Sorting |  | Pass
Pagination |  | Pass
Search |  | Fail
Filter |  | Fail
User Master
Add |  | Fail
Edit |  | Pass
Delete |  | Pass
Sorting |  | Pass
Pagination |  | Pass
Reset password |  | Pass
Teacher Management
Add |  | Fail
Edit |  | Pass
Delete |  | Fail
Sorting |  | Pass
Pagination |  | Pass
Reset password |  | Pass
Student Management
Add |  | Pass
Edit |  | Fail
Delete |  | Fail
Sorting |  | Fail
Pagination |  | Fail
Student Status Update
Filter |  | Pass
Search |  | Fail
Pagination |  | Pass
Student Section Mapping
Filter |  | Pass
Search |  | Fail
Pagination |  | Pass
Academic Eligibility Programs
Filter |  | Fail
Search |  | Pass
Pagination |  | Pass

## TEST CASE
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-ACADEMIC YEAR | TC_MAS_AY_01 | Verify that the Academic Year is created in the backend and displayed correctly in the frontend | Academic Year should be created successfully in the backend and displayed correctly in the frontend | Academic Year displayed correctly in the front end | FAIL | Month is not displayed in the Academic year
2 | MASTER-ACADEMIC YEAR-ROLL OUT | TC_MAS_AY_02 | Verify that the Rollout action is enabled after the Academic Year end month. | After the Academic Year end month is completed, the Rollout action should be enabled and availabl | Now Roll out action is not Displyed even the Academic year end Month is reached | FAIL
3 |  | TC_MAS_AY_03 | Verify that once select the Roll out then the next Academic Year automatically displayed | After the Roll out Next academic year Automatically listed | Next academic year listed after the Roll | FAIL | Next academic year listed but Revert option is not displayed in the current academy
4 |  | TC_MAS_AY_04 | Verify that Once Rollout then the Current Academic year Revert Action is displayed | Revert Action is displayed for the current academic year | Revert Action is displayed for the Current Academic Year | FAIL | Once revert and student is mapped to the section and then able to revert the student
5 |  | TC_MAS_AY_05 | Verify that After the Roll out Thenthe student Status is displayed as Promoted | Student status is displayed as Prompted after the Rollout | Student status is Displayed as Prompted after the Rollout | FAIL | Now the discontinued student status also changed to Active Once student is mapped to the section then Prompted status is listed in edit and view mode
6 |  | TC_MAS_AY_06 | Verify that After the Roll out then the Student is Mapped to the Student Section mapping section | Once student is rollout then the Student is mapped to the Student section Mapping | After the roll out If the student is mapped to the Student Mapping section | FAIL | Old section students are not listed
7 |  | TC_MAS_AY_07 | Verify that After the Roll out ,then the student section mapping old section is selected then the student name is listed | Student names are listed when select the previous Section selected | Student names are not listed when select the old section | FAIL
8 |  | TC_MAS_AY_08 | Verify that after roll outand Student mapped to the next section Corresponding section video is listed in the student portal | In student portal After the rollout ,Corresponding Std video is listed in the student portal | After rollout not able to mapping the section | FAIL
9 |  | TC_MAS_AY_09 | Verify that After the roll out and only one student mapped to the next section then the Revert option should not be listed in the Current academic year | Revert action is should not be listed after only one student is mapped to the next section | Now Always displayed the Revert action in current academic year after the roll out | FAIL | Always displayed the Revert action for the Current Academic year
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER -STANDARD | TC_STD_01 | Verify that the Standard is created in the backend and displayed in the frontend. | Standard should be created successfully in the backend and displayed correctly in the frontend. | Standard is creaded by theBackend team and it's listed correctly in the Front End | PASS
2 |  | TC_STD_02 | Verify that the Search functionality works correctly in the Standard module. | Search should Displayed correct Standard records based on the search input. | Searching standard is working Correctly | PASS
3 |  | TC_STD_03 | Verify that the Sorting functionality works correctly in the Standard Master. | Standards should be sorted correctly based on the selected sorting order. | Ascending order displayed incorrectly | FAIL | Select ascending order but IX Std listed first
4 |  | TC_STD_04 | Verify that the Pagination works correctly in the Standard Master. | Records should be displayed correctly across pages as per pagination | Pagination Works correctly | PASS
5 |  | TC_STD_05 | Verify that the Filter functionality works correctly in the Standard Master. | Filter should display only the relevant Standard records based on the selected criteria. | Filter works correctly | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-GROUP | TC_GROUP_01 | Verify Add Group popup opens on clicking Add Group button | Add Group popup should open | group is Added Successfully | PASS
2 |  | TC_GROUP_02 | Verify Standard field is mandatory | Select the Standard Field | Standard Field is Selected successfully | PASS
3 |  | TC_GROUP_03 | Verify Group Name field is mandatory | Enter the Group name | Grou name is entered successfully | PASS
4 |  | TC_GROUP_04 | Verify Group Name in Tamil field is mandatory | Enter the Group name in Tamil | Tamil name is entered successfully | PASS
5 |  | TC_GROUP_05 | Verify user can select Standard | Selected standard should be Added | Standard selected successfully | PASS
6 |  | TC_GROUP_06 | Verify that Enter all mandatory fields and click on Save. | The data should be saved successfully and a confirmation message should be displayed. | Group is added successfully | PASS
7 |  | TC_GROUP_07 | Verify the behavior when any one mandatory field is left empty. | System should display a validation message and prevent saving until all mandatory fields are filled. | Message displayed | PASS
8 |  | TC_GROUP_08 | Verify that after clicking the Save button, the saved data is listed in the list. | The newly saved data should appear correctly in the list. | Saved group is listed in the group | PASS
9 |  | TC_GROUP_09 | Verify that when the Cancel button is clicked in the Group, the data is not saved or listed in the list. | The data should not be saved, and it should not appear in the list. | Cancel button is selected then the Data is not saved | PASS
10 |  | TC_GROUP_10 | Verify that after clicking the Save button, the "Add Another Group" popup is displayed. | The "Add Another Group" popup should appear, allowing the user to add a new group. | Add another pop up Displayed correctly | PASS
11 |  | TC_GROUP_11 | Verify that by selecting the "Add Another Group" popup, a new group can be created. | The user should be able to create a new group successfully through the "Add Another Group" popup, and it should be listed in the group list. | New group can be created successfully | PASS
12 |  | TC_GROUP_12 | Verify that the Group Name is unique when creating a new group. | The system should not allow duplicate group names and should display a validation message if the name already exists. | System not allowed the duplicate group | PASS
13 |  | TC_GROUP_13 | Verify that a Group can be edited in the Master. | The system should allow updating the Group details, and the changes should be reflected correctly in the Group list. | Group is successfully edited | PASS
14 |  | TC_GROUP_14 | Verify that a Group can be deleted in the Master. | The selected Group should be removed from the list, and a confirmation message should be displayed. | Once group is not mapped then able to delete | PASS
15 |  | TC_GROUP_15 | Verify the Search functionality in the Group Master. | The system should Displayed correct Group records based on the search input. | Searching is working as expected | PASS
16 |  | TC_GROUP_16 | Verify that filter by Group Name shows only matching groups | Only groups with matching Group Name are displayed | Tamil font not accepted in Group name field (Copy & Paste not working) | FAIL
17 |  | TC_GROUP_17 | Verify that filter by Standard shows only groups of selected standard | Only groups with selected Standard (e.g., XI) are displayed | Filter is working correctely | PASS
18 |  | TC_GROUP_18 | Verify that filter works correctly when both Group Name and Standard are applied | Only groups matching both Group Name and Standard are displayed | Filter is worked correctly when select the Both group name and std | PASS
19 |  | TC_GROUP_19 | Verify that Reset button clears all filter fields and shows all groups | All filter inputs are cleared and full list of groups is displayed | Reset all the selected Data | PASS
20 |  | TC_GROUP_20 | Verify filter behavior when no matching groups found | Display message like "No records found" or show empty list | No records found message displayed | PASS
21 |  | TC_GROUP_21 | Verify that sorting functionality works in Group Master | Groups should be sorted correctly by Group Name, Standard, etc. | Sorting is Working correctly | PASS
22 |  | TC_GROUP_22 | Verify that pagination works correctly in Group Master | Records should be displayed properly across pages as per settings | Pagination works correctly | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-SECTION | TC_MAS_SEC_01 | Verify that the Section Master page loads successfully | Section Master page should load successfully with section list displayed | Section Master Page loaded successfully | PASS
2 |  | TC_MAS_SEC_02 | Verify Add Section button is visible in Section Master page | Add Section button should be visible and enabled | Add section button is visibled and select cickable | PASS
3 |  | TC_MAS_SEC_03 | Verify Add Section popup opens on clicking Add Section button | Add Section popup should open with Section Name field | Add section Pop up opened successfully | PASS
4 |  | TC_MAS_SEC_04 | Verify Section Name field is mandatory | Validation message should be displayed when Section Name is empty | Message displayed | PASS
5 |  | TC_MAS_SEC_05 | Verify user can add a new section with valid Section Name | Section should be added successfully | Section is added successfully | PASS
6 |  | TC_MAS_SEC_06 | Verify success message after adding a section | “Section added successfully” message should be displayed | After saved then the message displayed | PASS
7 |  | TC_MAS_SEC_07 | Verify newly added section appears in the section list | New section should be displayed in the list | Created section is listed correctly | PASS
8 |  | TC_MAS_SEC_08 | Verify default status of newly added section | Status should be set to Active by default | Default added section status is displayed as asctive | PASS
9 |  | TC_MAS_SEC_09 | Verify Add Another Section button in success popup | Add Section popup should reopen | After save add another Section Pop up displayed successfully | PASS
10 |  | TC_MAS_SEC_10 | Verify duplicate Section Name validation | System should not allow duplicate section names | Not allowed to enter Duplicate Section name | PASS
11 |  | TC_MAS_SEC_11 | Verify Edit section functionality | Section details should be updated successfully | Edited section successfully | PASS
12 |  | TC_MAS_SEC_12 | Verify Delete section functionality | Section should be deleted after confirmation | Once section is mapped then unable to deleted | PASS
13 |  | TC_MAS_SEC_13 | Verify Search functionality in Section Master | Search should display matching section records | Search functionality works Correctly | PASS
14 |  | TC_MAS_SEC_14 | Verify Pagination works correctly in Section Master | Records should display correctly across pages | Pagination works correctly | PASS
15 |  | TC_MAS_SEC_15 | Verify Section Name filter field is displayed | Section Name filter field should be displayed | Filter is worked for the selected filter data | PASS
16 |  | TC_MAS_SEC_16 | Verify Status filter dropdown is displayed | Status filter dropdown should be displayed | Active and inactive filter dropdown displayed | PASS
17 |  | TC_MAS_SEC_17 | Verify filter by Section Name with valid input | Only matching section records should be displayed | Matching records are Filtered successfully | PASS
18 |  | TC_MAS_SEC_18 | Verify filter by Active/Inactive status | Only Selected Active/Inactive sections should be displayed | Matching records are Filtered successfully | PASS
19 |  | TC_MAS_SEC_19 | Verify combined filter using Section Name and Status | Records matching both filters should be displayed | Combined filter works correctly | PASS
20 |  | TC_MAS_SEC_20 | Verify filter with invalid Section Name | No records should be displayed | No records found message displayed | PASS
21 |  | TC_MAS_SEC_21 | Verify clearing Section Name filter | All section records should be displayed | All selected data is cleared | PASS
22 |  | TC_MAS_SEC_22 | Verify clearing Status filter | All section records should be displayed | All status filter Displayed correctly | PASS
23 |  | TC_MAS_SEC_23 | Verify filter works along with pagination | Filtered records should be paginated correctly | Pagination works correctly | PASS
24 |  | TC_MAS_SEC_24 | Verify sorting works along with Section Name | Sorting is correctly displayed in Ascending,Decending order in the list | Sorting is Working correctly | PASS
25 |  | TC_MAS_SEC_25 | Verify sorting works along with Status | Sorting is correctly displayed in Active/Inactive in the list | Sorting works correctly with the Active and inactive status | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-SECTION MAPPING | TC_MAS_SMAP_01 | Verify Section Mapping page loads successfully | Section Mapping page should load with list of mapped records | Section mapping page loaded successfully | PASS
2 |  | TC_MAS_SMAP_02 | Verify Add Mapping button is visible | Add Mapping button should be visible and enabled | Add mapping button is visibled | PASS
3 |  | TC_MAS_SMAP_03 | Verify Add Section Mapping popup opens on clicking Add Mapping | Add Section Mapping popup should open | Add mapping is selected then Add Subject mapping is Opened successfully | PASS
4 |  | TC_MAS_SMAP_04 | Verify that the Academic Year field is mandatory, read-only, and automatically loaded | Academic Year field should be mandatory, read-only, and auto-populated with the current academic year | Now not displayed the Academic year | FAIL
5 |  | TC_MAS_SMAP_05 | Verify that the Standard, Group, Section, and Medium fields in Section Mapping are selectable from the dropdown | Standard, Group, Section, and Medium dropdowns should display options and allow selection | All fields are selected from the drop down | PASS
6 |  | TC_MAS_SMAP_06 | Verify that all mandatory fields are entered in the Section Mapping screen. | Section Mapping should be saved successfully without validation errors | Entere all the fields and saved succuessfully | PASS
7 |  | TC_MAS_SMAP_07 | Verify that when any one mandatory field is left unselected in the Section Mapping screen | Validation message should be displayed and save action should be blocked | Message displayed | PASS
8 |  | TC_MAS_SMAP_08 | Verify newly added mapping appears in the list | New mapping record should be displayed in the list | Created subject mapping is listed | PASS
9 |  | TC_MAS_SMAP_09 | Verify Edit Section Mapping functionality by changing only the Status and Medium fields. | Section Mapping should be updated successfully with the modified Status and Medium while other fields remain unchanged. | Subject mapping is updated successfully | PASS
10 |  | TC_MAS_SMAP_10 | Verify Delete Section Mapping functionality | Mapping should be deleted after confirmation | Once mapping the unit then not able to Delete | PASS
11 |  | TC_MAS_SMAP_11 | Verify duplicate Section Mapping validation | System should not allow duplicate section mapping | Duplicate subject mapping is not allowed,Message displayed | PASS
12 |  | TC_MAS_SMAP_12 | Verify combined filter functionality | Records matching all selected filters should be displayed | Filter functionality is working correctly | PASS
13 |  | TC_MAS_SMAP_13 | Verify Reset button clears all filters | All filters should be cleared and full list displayed | Reset is selected then the selected data is cleared | PASS
14 |  | TC_MAS_SMAP_14 | Verify sorting functionality in the Section Mapping screen. | Records should be sorted correctly based on the selected column in ascending and descending order. | Status field Sorting is not working | FAIL | Status sorting is not working
15 |  | TC_MAS_SMAP_15 | Verify pagination in Section Mapping list | Records should be displayed correctly across pages | Pagination works correctly | PASS
16 |  | TC_MAS_SMAP_16 | Verify Search functionality in the Section Mapping screen. | Search should display records that match the entered keyword. | Tamil subject name search functionality is not working | FAIL | Tamil Subject name is not listed
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-CO CURRICULUM CATEGORY | TC_MAS_COCURR_01 | Open Co-Curriculum Category page | Co-Curriculum Category page should load successfully | Co-curriculum page load successfully | PASS
2 |  | TC_MAS_COCURR_02 | Click Add Category button | Add Category popup/page should open | Add Button is clickable and Pop up opened | PASS
3 |  | TC_MAS_COCURR_03 | Enter valid category name and save | Category should be saved and listed with Active status | Valid Category name accepts | PASS
4 |  | TC_MAS_COCURR_04 | Try saving without entering category name | Validation message should be displayed | Error message displayed"Highlight fields required" | PASS
5 |  | TC_MAS_COCURR_05 | Add a duplicate category name | System should not allow duplicate category and show error message | Error message displayed"Already Exists" | PASS
6 |  | TC_MAS_COCURR_06 | Verify newly added category in the list | Newly added category should appear in the category list | Newly added Category is listed in the list | PASS
7 |  | TC_MAS_COCURR_07 | Click Edit icon for a category | Category details should be displayed in Edit mode | Edit the Staus in Edit mode | PASS
8 |  | TC_MAS_COCURR_08 | Click Delete icon for a category | Confirmation popup should be displayed | Deleted the Category once before mapping subjects to the category.Once subject is mapped not able to delete | PASS
9 |  | TC_MAS_COCURR_09 | Verify that Inactive category then not displayed the Drop down in the List | Inactive Category is not listed in the Dropdown | Inactive Category is not listed in the Drop down | PASS
10 |  | TC_MAS_COCURR_10 | Verify that the Search Functionality in Co-curriculum category | When a keyword is entered in the search field, the system should display only the co-curriculum records that match the searched keyword. | The system displays only the co-curriculum records matching the entered search keyword. | PASS
11 |  | TC_MAS_COCURR_11 | Verify that the Filter Functionality in Co-curriculum category | When filter options are applied, the system should display co-curriculum records based on the selected filter criteria. | The system displays co-curriculum records according to the selected filter options. | PASS
12 |  | TC_MAS_COCURR_12 | Verify that the Pagination in the Co-curriculum category | When pagination controls are used, the system should correctly navigate and display co-curriculum records page by page as per the selected page number and rows per page. | The system correctly navigates between pages and displays co-curriculum records based on pagination settings. | PASS
13 |  | TC_MAS_COCURR_13 | Verify that the sorting in the Cocurriculum Category | When sorting is applied, the system should display co-curriculum records in the selected ascending or descending order. | The system displays co-curriculum records in the applied sorting order. | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-SUBJECT | TC_MAS_SUB_01 | Verify Subject List Display | The Subject Master page should display all subjects with Subject Name, Category, Updated By, and Status. | All subjects are displayed correctly with Subject Name, Category, Updated By, and Status. | PASS
2 |  | TC_MAS_SUB_02 | Verify Add Subject Popup | When clicking Add Subject, the Add Subject popup should open with Category, Category Type, Subject Name, and Subject Name in Tamil fields. | Add Subject popup opens successfully with all required fields. | PASS
3 |  | TC_MAS_SUB_03 | Verify Mandatory Field Validation | If mandatory fields (Category, Category Type, Subject Name, Subject Name in Tamil) are not filled and Save is clicked, validation error messages should be displayed. | Validation messages are displayed for mandatory fields. | PASS
4 |  | TC_MAS_SUB_04 | Verify Category Selection | When a Category is selected, the Category Type dropdown should be enabled and display relevant values. | Curriculum,co-curriculum and Extra curriculum category is listed in the dropdown | PASS
5 |  | TC_MAS_SUB_05 | Verify Add New Subject | After entering valid details and clicking Save, the subject should be added successfully and displayed in the subject list. | The subject is added successfully and displayed in the list. | PASS
6 |  | TC_MAS_SUB_06 | Verify Duplicate Subject Restriction | System should not allow adding a duplicate subject name under the same category. | System prevents duplicate subject creation and displays an error message as:Subject name already exists" | FAIL | Message Displayed as Subject Tamil Name already exists but i enter Both the english and Tamil Name for the existing name
7 |  | TC_MAS_SUB_07 | Verify Edit Subject | When clicking the Edit icon, the subject details should be displayed in editable mode and updates should be saved successfully. | Subject details are loaded correctly and updated successfully. | PASS | Corresponding all field /Section edited name is displayed correctly
8 |  | TC_MAS_SUB_08 | Verify Delete Subject | When clicking the Delete icon, a confirmation message should appear and the subject should be removed after confirmation. | Confirmation message is displayed and subject is deleted successfully. | PASS
9 |  | TC_MAS_SUB_09 | Verify Subject Status | Subject status should be displayed correctly as Active or Inactive. | Subject status is displayed correctly. | PASS | Once inactive then the Subject is not listed in the Subject mapping
10 |  | TC_MAS_SUB_10 | Verify Search Functionality | When a keyword is entered in the search box, matching subjects should be displayed. | Only matching subjects are displayed based on the search keyword. | FAIL | Tamil Subject name
11 |  | TC_MAS_SUB_11 | Verify Sorting Functionality | When sorting is applied on Subject Name or Category, the subjects should be listed in ascending or descending order. | Subjects are listed correctly based on the selected sorting order. | PASS
12 |  | TC_MAS_SUB_12 | Verify that once Subject is mapping then not allow to delete the Subject | Subject is mapped to the Subjectmapping then not allow to delete the Subject | Once subject is mapping then the Delete the Subject Error message displayed as"Cannot delete: Subject is mapped in class-subject mapping" | PASS
13 |  | TC_MAS_SUB_13 | Verify that Once Co-curriculum category is selected then the Category type is visible other wise is it not visible | Once select Co-curriculm Category is selected then the type is visible | Once selected co-curriculum category then Category type is visible | PASS
14 |  | TC_MAS_SUB_14 | Verify that once Subject is mapped in the Subject mapping then not allowed to delete the Subject | Once Subject is mapped in the Subject Mapping then the Subject shoud not be allow delete | Mapped the subject is cannot be Deleted .Message displayed as "Cannot delete: Subject is mapped in class-subject mapping" | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-SUBJECT MAPPING | TC_MAS_SUBMAP_01 | Verify that the Subject mapping list page displayed correctly with all column(Action,std&Group,Category,Subjects,Updated by) | Subject Mapping page is listed with all Header | Subject Mapping List page displayed with all Headers | PASS
2 |  | TC_MAS_SUB MAP_02 | Verify that ADD MAPPING Button is visible and clickable then the Subject mapping page is displayed | Add Mapping button is visible and And clickable then the Subject mapping page displayed | Subject mapping page is opened correctly when select the Add Mapping button | PASS
3 |  | TC_MAS_SUB MAP_03 | Verify that Mapping page is displayed with Category,Co-curriculum category and Std &Group and Mapping summary is displayed | Mapping page is displayed with the Correct fields | Mapping page is displayed with correct field | PASS
4 |  | TC_MAS_SUB MAP_04 | Verify that select the Category then the corresponding Subject name check box is listed in the Page | Selecte the Category then the corresponding subject is Displayed correctly | Selected category then the Active subject name is displayed correctly | PASS
5 |  | TC_MAS_SUB MAP_05 | Verify that once select the Co-curriculum then the Category type is visible otherwise this field is disabled | Select the Co-curriculum field then the category is displayed | co-curriculum category is selcted then the category type is visibled other category is selected then Disable the Category type | PASS
6 |  | TC_MAS_SUB MAP_06 | Verify that Mapping the Subject to the Standard | Subject is Mapped to the Standard | Selected subject is mapped to the Standard | PASS
7 |  | TC_MAS_SUB MAP_07 | Verify that selected subject is listed in the Student Portal | Selected subjects are listed in the student portal | Selected subjects are Listed in the Student portal | PASS
8 |  | TC_MAS_SUB MAP_08 | Verify that the selected subjects are displayed in the Mapping summary | Selected subjects are listed in the Mapping summary section | Selected Subjects are listted in the mapping summary section page | PASS
9 |  | TC_MAS_SUB MAP_09 | Verify that Inactive subject names are not listed in the newly added mapping section | After Inactive subjects then the subject is not listed in the Subject section | Inactive subject names are not listed in the Newly added subject mapping | PASS
10 |  | TC_MAS_SUB MAP_10 | Verify that Inactive Subject names are not listed in the Subject mapping section in edit mode | subject is not mapping in the std then the subject is inactive ,If the subject is not listed in edit Mode | Edit mode,Inactive subject is listed | FAIL
11 |  | TC_MAS_SUB MAP_11 | Verify that once Subject is mapping then the subject is inactive at that time Subject name is listed in the Edit mode | Once subject is mapping then the subject is inactive at that time Subject is listed in edit mode | After mapping then inactive subject then the Subject is listed in edit mode | PASS
12 |  | TC_MAS_SUB MAP_12 | Verify that Should not be allow delete if the Subject mapping under the unit | Subject is mapped and not able to deleted | Unable to deleted once the subject is mapped under the Unit | PASS
13 |  | TC_MAS_SUB MAP_13 | Verify that Should be allow deletion when there is no unit is mapped this subject | Subject is deleted when there is no unit is mapped | Deleted the Subject mapping,once not mapping the unit under this subject | PASS
14 |  | TC_MAS_SUB MAP_14 | Verify that once video is published then the subject name is should not be changed | Subject name is Not changed when the video is published for the subject | Now able to deselect the subject name when if the video is Published | FAIL
15 |  | TC_MAS_SUB MAP_15 | Verify that delete the subject mapping when there is no unit,topic is mapped this subject | Deletion is allowed when there is no unit is mapped for this subject | Deletion is allowed when there is no Unit is mapped for this subjects | PASS
16 |  | TC_MAS_SUB MAP_16 | Verify that check the Search functionality in the Subject mapping | When a keyword is entered in the search box, matching standard should be displayed. | Only matching Std are displayed based on the search keyword. | FAIL | Extra-Curriculum search not working
17 |  | TC_MAS_SUB MAP_17 | Verify that the Filter functionality in the subject mapping | Filter by Category,std and Category Type | Filtered by Std,Category and Category Type is working fine correctly | PASS
18 |  | TC_MAS_SUB MAP_18 | Verify that the Pagination in the subject mapping | When pagination controls are used, the system should correctly navigate and display Subject mapping records page by page as per the selected page number and rows per page. | Pagination works correctly in the Subject Mapping | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-UNIT | TC_MAS_UNIT_01 | Verify Unit Master page loads successfully | Unit Master page should load without errors and display unit list | Unit Master page Loaded sucessfully | PASS
2 |  | TC_MAS_UNIT_02 | Verify “Add Unit” button visibility | “Add Unit” button should be visible and enabled | Add unit button is visibled and clickable then the unit pop up opened | PASS
3 |  | TC_MAS_UNIT_03 | Verify Category dropdown values | Category dropdown should list valid options (Curriculum, Co-curriculum, Extra-curriculum) | Category drop down is listed correctly based on select the category | PASS
4 |  | TC_MAS_UNIT_04 | Verify Standard & Group selection | Standard & Group dropdown should list available standards | Standard and group is listed for the active Std | PASS
5 |  | TC_MAS_UNIT_05 | Verify Subject Name dropdown based on selected standard | Subject Name dropdown should list subjects related to selected standard | Subject is listed based on the Selected std | PASS
6 |  | TC_MAS_UNIT_06 | Add unit with all mandatory fields filled | Unit should be saved successfully and listed in Unit Master grid | Unit master is successfully saved | PASS
7 |  | TC_MAS_UNIT_07 | Try to save unit without mandatory fields | System should show validation message and not save | Leave any one mandatory field then error message displayed as"Highlights fields are required" | PASS
8 |  | TC_MAS_UNIT_08 | Verify English and Tamil unit title display | Unit Title should display both English and Tamil names correctly | Unit title is entered for the Both english and Tamil | PASS
9 |  | TC_MAS_UNIT_09 | Add duplicate unit title for same subject and standard | System should not allow duplicate unit and show error message | Duplicate unit is not allowed
10 |  | TC_MAS_UNIT_10 | Verify unit status after creation | Newly added unit status should be Active by default | Once status Creation default it is displayed as Active | PASS
11 |  | TC_MAS_UNIT_11 | Click Edit icon for a unit | Selected unit details should open in edit mode | Unit details are updated in Edit Mode | PASS
12 |  | TC_MAS_UNIT_12 | Verify that after the Video upload cannot be edit the Std | Once video is upload for the particularUnit then not able to edit theStandard in the unit Master | Not able to changed the Std when if any one video is upload for this unit | FAIL | After video upload restrict unit inactive
13 |  | TC_MAS_UNIT_13 | Change unit status from Active to Inactive | Unit status should change to Inactive successfully | Unit status changed correctly | PASS
14 |  | TC_MAS_UNIT_14 | Verify inactive unit display | Inactive unit should be clearly marked as Inactive | Inactve Unit is not listed for the create the Topic drop down | PASS
15 |  | TC_MAS_UNIT_15 | Verify that once video is upload then should not be allow to Change the Status | Video is uploaded then the Unit is not able to inactive | Message displayed | PASS | Now once published then inactive the uploaded videos
16 |  | TC_MAS_UNIT_16 | Click Delete icon for a unit | Confirmation popup should be displayed | Confirmation pop up displayed | PASS
17 |  | TC_MAS_UNIT_17 | Verify that after the video is published then the Unit is should not be allow to delete | Video is Uploaded then the unit is not able to deleted | Not able to deleted | PASS
18 |  | TC_MAS_UNIT_18 | Verify search functionality | Search should return matching unit records | Matching search keyword listed correctly | PASS
19 |  | TC_MAS_UNIT_19 | Verify sorting by Category | Units should be sorted correctly based on Category | Sorting is working correctly in the Unit Master | PASS
20 |  | TC_MAS_UNIT_20 | Verify the Pagination functionality | Pagination is working correctly | Pagination works correctly and navigate to the corressponding page | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-TOPIC | TC_MAS_TOPIC_01 | Verify Topic Master page loads successfully | Topic Master page should load without errors | Topic Master page loaded successfully without errors | PASS
2 |  | TC_MAS_TOPIC_02 | Verify list grid columns | Grid should display all required columns | All columns (Action,Category,Std &group,Subject name,Unit title,Topic Title Updated by,Status) are displayed correctly in the list grid | PASS
3 |  | TC_MAS_TOPIC_03 | Verify topic records display | Existing topic records should be listed | Topic records displayed correctly | PASS
4 |  | TC_MAS_TOPIC_04 | Verify Add Topic button | Clicking Add Topic should open popup | Add Topic popup opened successfully | PASS
5 |  | TC_MAS_TOPIC_05 | Save without selecting Category | Validation message should appear | Validation message displayed | PASS
6 |  | TC_MAS_TOPIC_06 | Verify that enter all the Mandatory field and click on save | All mandatory fields are Entered and saved successfully | All mandatory fields are ENtered successfully | PASS
7 |  | TC_MAS_TOPIC_07 | Verify that category dropdown and Category type | Once co-curriculum is selected then the Category type is Visibled.Otherwise category type is not visible in the Tpoic master | Once co-curriculum category is selected then the category type is Vsibled | PASS
8 |  | TC_MAS_TOPIC_08 | Verify that selected std then corresponding mapped subjects and unit is listed in the dropdown | Corresponding selected Std subjects and units are Listed in the drop down | Selected std then the corresponding subjects and Unit drop down is listed | PASS
9 |  | TC_MAS_TOPIC_09 | Verify that Enter topic title in Both English and Tamil Name | Topic titles are entered for english and Tamil medium student | Topic titles are entered for both english and Tamil language | PASS
10 |  | TC_MAS_TOPIC_10 | Verify that Check the Duplicate topic name | Enter already existing topic name | Error message displayed | PASS
11 |  | TC_MAS_TOPIC_11 | Verify that delete the Topic master | Delete is allowed only Before upload videos for this topic | Video is not upload for the corresponding Topic then the topic is able to deleted | PASS
12 |  | TC_MAS_TOPIC_12 | Verify that Should not be allowed deletion when the video is upload for the Particulur topic | Once video is upload for this Topic then unable to delete theTopic master | Message displayed as"Topic cannot be deleted because it is used in video uploads" | PASS
13 |  | TC_MAS_TOPIC_13 | Verify that edit the Topic and changes are updated for the Corresponding pages | Changes are updated in all the corresponding pages | Changes are updated succesfully | PASS
14 |  | TC_MAS_TOPIC_14 | Verify that once video is upload then the Edit for the Std is not allowed | Video is uploaded then cannot be edit the Std | Video uploaded successfully then cannot be edit the Std | PASS
15 |  | TC_MAS_TOPIC_15 | Verify that inactive topic is not listed in the Upload video section | Inactive Topic is not listed in the drop down | Inactive Topic is not listed in the dropdown | PASS
16 |  | TC_MAS_TOPIC_16 | Verify that already upload video for this topic thenthe Topic is not able to Inactive | Once video is upload thenthe topic is not able to inactive | Once video is uploaded then the Topic should not be Inactive | FAIL
17 |  | TC_MAS_TOPIC_17 | Verify that the search functionality fo the Topic master | When a valid keyword (Topic Title / Subject / Unit) is entered in the search field, the system should display only the matching topic records | Search returns only the relevant topic records and hides non-matching records | PASS
18 |  | TC_MAS_TOPIC_18 | Verify that the Filter functionality in the Topic master | When a filter option (Category / Standard / Subject / Unit/Topic /Status) is applied, the system should display only the topic records matching the selected filter criteria | Filter displays only the topic records matching the selected criteria | PASS
19 |  | TC_MAS_TOPIC_19 | Verify sorting functionality in Topic Master | When clicking on any column header (Topic Title / Unit Title / Subject / Status), the records should be sorted in ascending or descending order accordingly | Records are sorted correctly in ascending and descending order based on the selected column | FAIL | Descending status fail
20 |  | TC_MAS_TOPIC_20 | Verify pagination functionality in Topic Master | When the number of topic records exceeds the page limit, the records should be split across multiple pages and navigation (Next / Previous / Page number) should work correctly | Pagination works correctly and records are displayed properly across multiple pages | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-UPLOAD VIDEOS | TC_MAS_UPLOAD VIDEO_01 | Verify Videos page loads successfully | Videos page loads with Total Videos count and Video Duration displayed | Videos page loaded successfully with correct counts | PASS
2 |  | TC_MAS_UPLOAD VIDEO_02 | Verify video list grid display | Video list displays Category, Medium, Standard, Video Summary, No. of Videos, Updated By, Status | All columns displayed correctly | PASS
3 |  | TC_MAS_UPLOAD VIDEO_03 | Verify Upload Videos button | Clicking Upload Videos opens Upload Video popup | Upload Video popup opened successfully | PASS
4 |  | TC_MAS_UPLOAD VIDEO_04 | Verify mandatory fields in Upload Video popup | All mandatory fields are marked with * | Mandatory fields marked correctly | PASS
5 |  | TC_MAS_UPLOAD VIDEO_05 | Verify Category selection | Category dropdown loads and allows selection | Category selected successfully | PASS
6 |  | TC_MAS_UPLOAD VIDEO_06 | Verify dependent fields (Category Type, Medium, Standard, Subject, Unit, Topic) | Dependent dropdowns load based on selection | Dependent fields loaded correctly | PASS
7 |  | TC_MAS_UPLOAD VIDEO_07 | Save without mandatory fields | Validation message should be displayed | Validation messages displayed | PASS
8 |  | TC_MAS_UPLOAD VIDEO_08 | Upload video with valid data | Video uploads successfully | Video uploaded successfully | PASS
9 |  | TC_MAS_UPLOAD VIDEO_09 | Verify uploaded video in list | Uploaded video appears in video list | Video displayed in list | PASS
10 |  | TC_MAS_UPLOAD VIDEO_10 | Verify default video status | Newly uploaded video status should be Not Published | Newly added video status is displayed as Not Published | PASS
11 |  | TC_MAS_UPLOAD VIDEO_11 | Verify Number of Views count | Video view count increases after Published the video | Video view count increases after Published the video | FAIL | Number of view counts displayed incorrectly
12 |  | TC_MAS_UPLOAD VIDEO_12 | Verify that Publish uploaded video | Selected video gets published successfully | Video published successfully | PASS
13 |  | TC_MAS_UPLOAD VIDEO_13 | Verify Published status | Status changes from Not Published to Published | Status updated to Published | PASS
14 |  | TC_MAS_UPLOAD VIDEO_14 | Verify that the uploaded video is not editable after publishing | Published video is cannot be edited | Published Video is cannot be edited | FAIL | Once video is published then edit the Uploaded videos
15 |  | TC_MAS_UPLOAD VIDEO_15 | Verify that editing is allowed for videos with a ‘Not Published’ status | Edit is allowed to the Not published Status | Edit is allowed tot he Not published Status | PASS
16 |  | TC_MAS_UPLOAD VIDEO_16 | Verify that only one video can be uploaded for a single topic | Only one video is uploaded for the Single Topic | Only one video is Uploaded for the Single Topic | PASS
17 |  | TC_MAS_UPLOAD VIDEO_17 | Verify that a new video can be uploaded for the same topic after the existing video is marked inactive | Video is replaced for the already Published video is successfully | Video is Replaced for Already Published Video | PASS
18 |  | TC_MAS_UPLOAD VIDEO_18 | Verify that once a published video is marked inactive, the video can be edited. | Once inactive Published videos then replace another video for the Same topic | Once inactive Published videos then replace another video then it is listed under the Not published status | PASS
19 |  | TC_MAS_UPLOAD VIDEO_19 | Verify that when a video status is changed from Inactive to Active, the newly edited video is listed under ‘Not Published’ | Once published replaced video then the changes are reflected in the student portal | Once published Replaced Video then the Changes are reflected | PASS
20 |  | TC_MAS_UPLOAD VIDEO_20 | Verify that a published video cannot be deleted | Published video cannot be deleted | Published video cannot be deleted | PASS
21 |  | TC_MAS_UPLOAD VIDEO_21 | Verify that deletion is allowed for videos with a ‘Not Published’ status. | Allow delete for the Not published video | Deletion s allowed for the Not published status | PASS
22 |  | TC_MAS_UPLOAD VIDEO_22 | Verify that if a video is already uploaded for a topic, a message is displayed when attempting to upload another video for the same topic | Message displayed already video exist | already video exist | PASS
23 |  | TC_MAS_UPLOAD VIDEO_23 | Verify that in edit mode, when the status is ‘Not Published,’ the Publish button is enabled | Publish button is enabled for the Not published status | Publish button is visible in the Edit mode.Once video published then the Public is is Hide | PASS
24 |  | TC_MAS_UPLOAD VIDEO_24 | Verify that the standard (Std) cannot be changed for an uploaded video in edit mode | Not changed the std for the already upload video in edit mode | Not changed std for the Already upload video in edit mode | FAIL | Now in inactive and change the std in edit mode
25 |  | TC_MAS_UPLOAD VIDEO_25 | Verify that if a published video is inactive, it is not listed in the student portal | Inactive video is not displayed in the student portal | Inactive video is Not displayed in the student portal | PASS
26 |  | TC_MAS_UPLOAD VIDEO_26 | Verify that Inactive Upload video then can change the video in edit mode | Replace the uploaded video in edit mode | Replaced the Uploaded video in edit mode | PASS
27 |  | TC_MAS_UPLOAD VIDEO_27 | Verify that Inactive then newly added the video at that time Student portal video is displayed for the newly even previousely student watch the video again second upload video at that time in number view count is should be in zero | Number of view count is displayed correctly | Number of view count is displayed Incorrectly | FAIL
28 |  | TC_MAS_UPLOADED VIDEO_28 | Verify that after the rollout, the previously uploaded videos from the previous academic year do not have any change in the number of views or the watched student count | Previous year uploaded video number of view count and Watched count displayed correctly | Once previous year watched student count is cleared Current academic Watched student count is not Displayed | FAIL
29 |  | TC_MAS_UPLOADED VIDEO_29 | Verify that after student watched the video then the Number of views count displayed | Verify that the number of views is incremented after a student watches a video. | VNumber of view count displayed incorrectly when the tamil medium video uploaded at that time English medium count also displayed | FAIL
30 |  | TC_MAS_UPLOADED VIDEO_30 | Verify that Select the Number of view count then the section wise student total counts,watched count and not watched count displayed | Number of view count is displayed correctly | Total students and Watched and not watched count is displayed correctly | PASS
31 |  | TC_MAS_UPLOADED VIDEO_31 | Verify that Select the Watched student count then the Student wise watched Time and status is displayed | Student last watched time and last watched video time is displayed | Student last watched time and last watched duration and status displayed correctly | FAIL | Once student completed to watched the video then the status displayed as compltely again student watched the same video status is changed to partilally completed
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-VIDEO STREAMING REPORT | TC_MAS_REPORT_01 | Verify Video Streaming Report page loads successfully | Video Streaming Report page is displayed successfully | Video Streaming Report page is displayed successfully. | PASS
2 |  | TC_MAS_REPORT_02 | Verify that student activity data is displayed correctly for This Day | Student activity graph shows only today’s video watch data. Watch Time tooltip displays correct date and duration (e.g., Jan 23 – 0 hr 4 min 0 sec). | Student activity for the current day is displayed correctly. | PASS
3 |  | TC_MAS_REPORT_03 | Verify that student activity data is displayed correctly for This Week. | Graph displays aggregated video watch activity for the current week. Dates and watch time are accurate. | Weekly video streaming data is displayed correctly. | PASS
4 |  | TC_MAS_REPORT_04 | Verify that student activity data is displayed correctly for This Month. | Graph displays video streaming activity for the current month. Watch time calculation is correct. | Monthly video streaming data is displayed correctly. | PASS
5 |  | TC_MAS_REPORT_05 | Verify that admin can filter video streaming data using calendar selection. | Graph updates based on the selected date/date range. Watch time matches the selected period. | Video streaming data is displayed correctly for the selected date range. | PASS
6 |  | TC_MAS_REPORT_06 | Verify watch time details are displayed on hover. | Tooltip displays: Date Watch Time in hh:mm:ss format | Tooltip displays correct date and watch time. | PASS
7 |  | TC_MAS_REPORT_07 | Verify that watch time is updated after a student watches a video. | Watch time is increased based on the actual duration watched by the student. | Watch time is updated correctly. | PASS
8 |  | TC_MAS_REPORT_08 | Verify cumulative watch time when multiple students watch videos | Total watch time equals the sum of all students’ watch durations. | Cumulative watch time is calculated correctly. | PASS
9 |  | TC_MAS_REPORT_09 | Verify the Back button navigation. | User is navigated to the previous page. | Navigation works as expected. | PASS
10 |  | TC_MAS_REPORT_10 | Verify that the system displays the student watched report category-wise. | The report displays student watch data only for the selected category. Student count, watch time, and view details are shown correctly category-wise. | Category-wise student watched report is displayed correctly. | FAIL
11 |  | TC_MAS_REPORT_11 | Verify accuracy of category-wise student watch data. | Student count, watch time, and views exactly match backend data. | Category-wise data matches the actual watch logs. | FAIL
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | MASTER-REORDER | TC_MAS_REORDER_01 | Verify Reorder Units & Topics page loads successfully | Reorder Units & Topics page is displayed. | Page loads successfully | PASS
2 |  | TC_MAS_REORDER_02 | Verify mandatory filter field validation | Validation messages are displayed for required fields (Category, Medium, Standard & Group, Subject). | Validation messages are displayed correctly. | PASS
3 |  | TC_MAS_REORDER_03 | Verify Category dropdown lists and selection. | Selected category is applied. Dependent fields are enabled accordingly. | Category selection works correctly. | PASS
4 |  | TC_MAS_REORDER_04 | Verify Medium dropdown functionality | Medium is selected and applied to the search. | Medium selection works correctly. | FAIL | Now there is not necessary in the Medium drop down Now Reorder Tamil Medium then English medium also order chaged
5 |  | TC_MAS_REORDER_05 | Verify Subject Name dropdown based on filters | Only relevant subjects are listed. | Subject list is filtered correctly. | FAIL | Co-curriculum subjects are not Listed
6 |  | TC_MAS_REORDER_06 | Verify Search displays units and topics. | Units and topics are displayed in reorderable list format. | Units and topics are displayed correctly. | PASS
7 |  | TC_MAS_REORDER_07 | Verify behavior when no units/topics are available. | Message “Null ” is displayed. | Null message is diplayed | PASS
8 |  | TC_MAS_REORDER_08 | Verify drag and drop reordering of units | Unit position changes visually. | Unit is reordered successfully. | PASS
9 |  | TC_MAS_REORDER_09 | Verify drag and drop reordering of topics within a unit | Topic order is updated. | Topic reorder works correctly. | PASS
10 |  | TC_MAS_REORDER_10 | Verify Save button functionality | Success message is displayed. Reorder changes are saved. | Once save the reorder then the changes are saved successfully. | PASS
11 |  | TC_MAS_REORDER_11 | Verify Cancel button functionality | Changes are discarded | Cancel works as expected. | PASS
12 |  | TC_MAS_REORDER_12 | Verify reordered units/topics reflect in Student Portal. | Units and topics are displayed in the reordered sequence. | Student portal reflects reordered sequence. | PASS
13 |  | TC_MAS_REORDER_13 | Verify Reset clears all selected filters. | All filter fields are cleared. Results section is reset. | Reset works correctly. | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | TEACHER MANAGEMENT | TC_TEACHER_01 | Verify that Teacher Managenment page loaded successfully | Teacher management page loaded successfully | Teacher management page loaded successfully | PASS
2 |  | TC_TEACHER_02 | Verify that Add Teacher button is visible and click able | ADD Teacher button is visibled | Add teacher button is visibled | PASS
3 |  | TC_TEACHER_03 | Verify that Enter all Mandatory field | Teacher Data saved successfully | Teacher data saved successfully | PASS
4 |  | TC_TEACHER_04 | Verify that leave any mandatory field | Message displayed already video exist | Highlights fields are required meaasage displayed | PASS
5 |  | TC_TEACHER_05 | Verify that Teacher mapped to the Current Academic information | Teacher is mapped to the Current Academy | Teacher is mapped to the current academy | PASS
6 |  | TC_TEACHER_06 | Verify that after the Rollout if the teacher academic Information is Diplayed correctly | After the rollout teacher current Academic information is displayed correctly | After rollout Teacher current Academic information is displayed correctly | PASS
7 |  | TC_TEACHER_07 | Verify that after rollout Current academic information Edit and Delete action is Visibled | After the Roll out Current academic information Edit and delete action is displayed | Edit and Delete options are Displayed in the Current academic year | PASS
8 |  | TC_TEACHER_08 | Verify that After roll out teacher academic information is displayed in Two separate line | Teacher Academic information dispalyed as two separte line | Teacher Academic Information as two separate line | PASS
9 |  | TC_TEACHER_09 | Verify that after roll out,if the teacher Std should not be changed | Teacher std should not be changed after the rollout | Teacher Std also changed | FAIL
10 |  | TC_TEACHER_10 | Verify that after roll out Previous year student data should not be listed | Student data is not listed in the Teacher portal after the roll out | Student data is not listed in the teacher portal after the rollout | PASS
11 |  | TC_TEACHER_11 | Verify that Once student section mapping then the student is listed in the current academic Teacher portal | Once student section mapping is completed then the Student is Listed in the teacher portal | In teacher portal ,after the section mapping if the student listed in the teacher portal | PASS
12 |  | TC_TEACHER_12 | Verify that After roll out if the teacher should be able to add new student via add student /Bulk upload | If the teacher able to add the student/bulk upload student After the roll out | After the roll out teacher is able to Add or bulk upload student | PASS
S.NO | MODULE/APPLICATIONS | TEST CASE ID | TEST CASE DESCRIPTIONS | EXPECTED RESULTS | ACTUAL RESULTS | STATUS | REMARKS
1 | STUDENT MANAGEMENT | TC_STUDENT_01 | Verify that if the teacher added or bulk upload the student | Teacher added or bulk uploaded the Student details | Teacher added to the Student successfully | PASS
2 |  | TC_STUDENT_02 | Verify that Current academic Information is displayed correctly | Student academic year displayed correctly | Student Academic information is displayed correctly | PASS
3 |  | TC_STUDENT_03 | Verify that if the student status is selected only active in the Add student | Only Active status is selected in the Add student /Bulk Uplod student | Only active student status is selected in Add student | FAIL | Initially Add student at that time Discontinued student is allowed
4 |  | TC_STUDENT_04 | Verify that if the student status is changed to Discontinued in edit mode | Student status is changed to discontinued in edit mode | Student status changed to discontinued in edit mode | PASS
5 |  | TC_STUDENT_05 | Verify that if the student Status is changed then the Academic history is displayed as separate line | Student academic history is displayed Correctly in separe line | Student Academic history is Displayed correctly in separate line | FAIL | last student status is displayed in the Academic information History
6 |  | TC_STUDENT_06 | Verify that if the student status is changed in Student status update section | student status is changed via Student status Updated section | Student status is changed via student status Updated section | PASS
7 |  | TC_STUDENT_07 | Verify that After the rollout then the student is Mapped to the next section student status is displayed as Prompted in edit mode | After roll out student and section mapping is done then the student status is displayed as Prompted in edit mode | Prompted status id displayed after the roll out and the student is mapped to the Another section | PASS
8 |  | TC_STUDENT_08 | Verify that Discontinued student is not listed in the Section mapping after the Roll out | Discontinued students are Not listed in the Next year section mapping | Now discontinued students are listed in the next year section mapping section | FAIL | After the rollout student status displayed as active in the list so duplicate in section mapping
9 |  | TC_STUDENT_09 | Verify that select the same date for discontinue then displayed in single entry | Select the same date for discontinue then displayed in the single entry | Same date is selected then the data is displayed in single line | PASS
10 |  | TC_STUDENT_10 | Verify that after the roll out,Student Std is Changed to the next standard in admin portal | After roll out Student std is changed | After roll out student std is changed | FAIL | Discontinued student also changed the Next standard
11 |  | TC_STUDENT_11 | Verify that After the Roll out ,If the student information is Should not be empty | After roll out student information should not be empty | Student information is empty | FAIL | Active /Discontinue student information is empty after the roll out . Once Next section mapping at that time student information is listed but roll number field is empty

## Sheet1
S.No | Module | Testcases | Result
1 | Student Status update | 1. Verify that student status can be updated using Student status update. (before rollout) 2. Verify that based on standard & Group selected Section & medium should loaded. 3. Verify that Standard & Group should be mandatory Section & Medium and Student name should not be mandatory. 4. Verify that based on selected standard & Group/selected Section & medium/ Student name data should be displayed after clicking Load button. 5. Verify that filter should clear after clicking Reset button 6. Verify that only active student should listed. 7. Verify that Single or multiple student status can be changed to Discontinued. 8. Verify that Change To and Date should be mandatory filed. 9. Verify that only Discontinued should be loaded in Change To dropdown. 10. Verify that after saving student as Discontinued it should reflect in Student Management. 11. Verify that student status should be updated. 12. Verify that status of the student can be changed using edit student option. 13. Verify that while rollout discontinued student should listed in preview student list. 14. Verify that while rollout discontinued student should not listed. | Fail | Point 11
2 | Student Section mapping | 1. Verify that after roll out section can be updated for the new standard using Student section mapping . 2. Verify that based on standard & Group selected Old Section & medium should loaded. 3. Verify that Standard & Group should be mandatory. 4. Verify that based on selected standard & Group/selected Old Section & medium data should be displayed after clicking Load button. 5. Verify that filter should clear after clicking Reset button 6. Verify that rollout student should listed. 7. Verify that Single or multiple student group/section can be changed. 8. Verify that Group or section should be mandatory filed. 9. Verify that after saving student as Section/ Group should reflect in Student Management. 10. Verify that Section of the student can be changed using edit student option. 11. Verify that after section mapping the students should list in their corresponding class teacher. | Fail | Roll out issue
3 | Academic Eligibility Programs | 1. Verify that Co curiculam, Extra curiculam can be added based on standard &group. 2. Verify that based on standard & Group selected Section & medium should loaded. 3. Verify that Standard & Group should be mandatory Section & Medium and Student name should not be mandatory. 4. Verify that based on selected standard & Group/selected Section & medium/ Student name data should be displayed after clicking Load button. 5. Verify that filter should clear after clicking Reset button 6. Verify that only active student should listed. 7. Verify that Single or multiple student status can be mapped. 8. Verify that Category should be mandatory filed. 9. Verify that Category type field should be appear if user select Co curriculum from category dropdown. 10. Verify that Category type, able to select and Save 11. Verify that Subject Name field should be appear if user select Extra curriculum from category dropdown. 12. Verify that subject name, able to select and Save. 13. Verify that after save, Standard & Group, category, Category Type/Subject, Student count details should list correctly. 14. Verify that based on the selected Co-curriculum/ Extra curriculum student should able to watch the updated video 15. Verify that only one academic eligibility program can be mapped to a Single student. | Fail
| Students | 1.Verify that student can be added using Add student option 2.Verify that multiple student can be added using Bulk upload option 3. Verify that after adding student, by default Active status should be updated. 4. Verify that Promoted status should updated if the student rollout . 5.Verify that discontinued status should updated if the studnt discontinued. 6.Verify that only active student should able to login and watch video. 7.Verify that photos for student can be uploaded bulkly. 8. Verify that student data can be edited. 9. Verify that student details should display correctly in the list. 10.Verify Search option on the page. 11.Verify filter option on the page. 12.Verify Sort option on the page.